## Project Plan
ADS 500B Project Plan |  |  |  | https://github.com/sregiphilip/ADS500B_FinalProject
Step | Task | Team Member | Ideal Date
Data Importing and Pre Processing | Import, wrangle, transform, and clean | Sanjay | 2021-07-25
| Code Clean Up | Maha | 2021-07-27
| Code Review | Luke | 2021-07-30
Data Analysis and Visualization | Identify, analyze, find correlations, and identify patterns | Maha | 2021-07-31
| Code Clean Up | Luke | 2021-08-02
| Code Review | Sanjay | 2021-08-04
Data Analytics | Determine need for learning method | Luke | 2021-08-06
| Code Clean Up | Maha | 2021-08-07
| Code Review | Sanjay | 2021-08-08
Presentation | Create Outline/Script | Sanjay | 2021-08-08
| Record | All team members | 2021-08-12 | 6:30pm

## Github
How to use Github
https://guides.github.com/activities/hello-world/